## Sheet1
WEEK | DAY | TASK
1 | 1 | Data Collection & EDA | Task-1: Load Kaggle “Credit Card Fraud Detection” dataset (284,807 txns, 492 frauds).
Task-2: PCA-transformed features (V1–V28) + Time + Amount analysis.
Task-3: Visualize fraud vs genuine in Amount, Time-of-day, 2D t-SNE/UMAP.
Task-4: Fraud rate by hour, transaction amount distribution.
Task-5: Interactive Plotly EDA dashboard + pandas-profiling report.
| 2 | Feature Engineering | Task-1: Create Time features: hour_of_day, night_flag, seconds_since_start.
Task-2: Amount scaling (StandardScaler + log transform).
Task-3: 50+ interaction & statistical features (V1*V3, V4/V12 ratio, rolling stats).
Task-4: PCA component interpretation using inverse transform.
Task-5: Save final feature set (train/test split by time).
| 3 | Baseline Classical Models | Task-1: Logistic Regression + XGBoost + LightGBM with scale_pos_weight.
Task-2: Handle imbalance: SMOTE, NearMiss, RandomUnderSampler.
Task-3: Evaluate AUC-ROC, AUC-PR, Precision@90%Recall, F1.
Task-4: Cross-validation with time-based split.
Task-5: Best baseline → AUC-PR ≥ 0.80.
| 4 | Anomaly Detection (Unsupervised) | Task-1: Isolation Forest, Autoencoder (Keras), One-Class SVM.
Task-2: Elliptic Envelope, Local Outlier Factor.
Task-3: Combine unsupervised scores as new features.
Task-4: Hybrid model beats pure supervised.
Task-5: Save best anomaly model.
| 5 | Deep Learning Models | Task-1: Simple MLP (3–5 dense layers + Dropout).
Task-2: TabNet + FT-Transformer.
Task-3: LSTM on sequence of last 10 transactions per card (synthetic sequences).
Task-4: Focal Loss + class weighting.
Task-5: Best deep model → AUC-PR ≥ 0.88.
2 | 1 | Final Ensemble & Threshold Tuning | Task-1: Stacking (XGBoost + TabNet + Autoencoder → meta).
Task-2: Calibrate probabilities + optimize threshold for max savings.
Task-3: Final model → Recall ≥ 0.94, Precision ≥ 0.90.
Task-4: Inference < 5ms.
Task-5: Save final production model (joblib).
| 2 | SHAP Explainability | Task-1: SHAP for every prediction (top 5 features).
Task-2: Force plot + summary dashboard.
Task-3: “Why this transaction was flagged?” report.
Task-4: Feature importance comparison across models.
Task-5: Export explainability notebook.
| 3 | Cost-Based Final Evaluation | Task-1: Apply realistic cost matrix (FP=$5, FN=$500).
Task-2: Optimize threshold for minimum total cost.
Task-3: Simulate savings on full dataset.
Task-4: Confusion matrix at optimal threshold.
Task-5: Final performance report.
| 4 | Real-Time Simulation | Task-1: Simulate streaming (1 txn per millisecond).
Task-2: Live prediction + alert system.
Task-3: Rolling AUC-PR monitoring.
Task-4: False positive rate control.
Task-5: Save live simulation log.
| 5 | Model Card & Submission Ready | Task-1: Complete Model Card (intended use, limitations, metrics).
Task-2: Fairness check on Amount bins.
3 | 1 | Streamlit – Real-Time Fraud Detector | Task-1: Build stunning Streamlit app titled “CreditSecure – Kaggle Fraud Detector”.
Task-2: Single transaction input form (Time, Amount, V1–V28).
Task-3: Instant prediction → Green (Genuine) / Red (Fraud) with probability.
Task-4: Live SHAP force plot + top 5 contributing features.
Task-5: Fraud risk meter + “Block / Allow” button.
| 2 | Streamlit – Batch & Live Dashboard | Task-1: CSV upload for batch prediction (up to 50k rows).
Task-2: Real-time confusion matrix + AUC-PR on uploaded data.
Task-3: Fraud vs Genuine amount/time distribution charts.
Task-4: Top 10 highest-risk transactions table.
Task-5: Download flagged transactions + SHAP explanations.
| 3 | Streamlit – Monitoring & Simulation | Task-1: Live streaming simulation using the full Kaggle test set.
Task-2: Rolling 1-hour metrics dashboard (Recall, Precision, Cost saved).
Task-3: Fraud alert sound + notification panel.
Task-4: Cost-saved counter ($ saved in real-time).
Task-5: Dark + banking professional theme.
| 4 | Deployment & Speed Optimization | Task-1: Deploy final app on Streamlit Community Cloud.
Task-2: Convert model to ONNX + 8-bit quantization.
Task-3: Full @st.cache_data + @st.cache_resource. Task-4: Inference < 8ms per transaction. Task-5: Share permanent public link + private share option.47CreditSecure35Final App Polish & Kaggle ShowcaseTask-1: Add “Trained on Kaggle Credit Card Fraud Dataset” banner + dataset link. Task-2: Add Kaggle notebook link + final AUC-PR score. Task-3: Beautiful landing page with project abstract. Task-4: Mobile-responsive UI. Task-5: Final ultra-fast deployed version.47CreditSecure41End-to-End Pipeline & One-Click RetrainTask-1: Build complete Scikit-learn + TensorFlow pipeline (preprocess → train → predict). Task-2: retrain.py script (downloads Kaggle data → trains → saves model). Task-3: predict.py for single/batch inference. Task-4: requirements.txt + Dockerfile. Task-5: Full pipeline documentation.47CreditSecure42Final Validation & Leaderboard ComparisonTask-1: Final 5-fold + time-based CV results. Task-2: Compare with top 100 Kaggle submissions (AUC-PR). Task-3: Cost-saved simulation on full 284k transactions. Task-4: Final metrics table + graphs. Task-5: Executive one-page summary.47CreditSecure43Documentation & PipelinesTask-1: Create a detailed project report covering objectives, methodology, data preprocessing, model evaluation, and key insights for future reference. Task-2: Draft a clear and concise README that includes project overview, installation instructions, usage guidelines, and key findings for easy accessibility. Task-3: Streamline model training by automating preprocessing, feature engineering, and hyperparameter tuning with Scikit-learn/TensorFlow Pipeline framework. Task-4: Develop scripts to automate data cleaning, transformation, and feature selection to ensure consistency and efficiency in model training. Task-5: Compile all documentation, insights, and findings into a well-structured report and share it with stakeholders or publish it for broader accessibility.47CreditSecure44Final Polish & PresentationTask-1: Record 4–6 minute professional demo video (live app + Kaggle results). Task-2: Prepare 12-slide presentation (problem → EDA → model → results → live app). Task-3: Final GitHub repo cleanup + badges. Task-4: Kaggle kernel/notebook submission ready. Task-5: Package everything into zip.47CreditSecure45Project Handover & DeliveryTask-1: Deliver live Streamlit link + full code + model + video. Task-2: Handover final report + Model Card + one-page summary. Task-3: Kaggle score screenshot + cost-savings proof. Task-4: 30-day support commitment. Task-5: Final handover email to company / professor / portfolio.
Task-4: Inference < 8ms per transaction.
Task-5: Share permanent public link .
| 5 | End-to-End Pipeline & One-Click Retrain | Task-1: Build complete Scikit-learn + TensorFlow pipeline (preprocess → train → predict).
Task-2: retrain.py script (downloads Kaggle data → trains → saves model).
Task-3: predict.py for single/batch inference.
Task-4: requirements.txt .
Task-5: Full pipeline documentation.
4 | 1 | Documentation & Pipelines | Task-1: Create a detailed project report covering objectives, methodology, data preprocessing, model evaluation, and key insights for future reference.
Task-2: Draft a clear and concise README that includes project overview, installation instructions, usage guidelines, and key findings for easy accessibility.
Task-3: Streamline model training by automating preprocessing, feature engineering, and hyperparameter tuning with Scikit-learn/TensorFlow Pipeline framework.
Task-4: Develop scripts to automate data cleaning, transformation, and feature selection to ensure consistency and efficiency in model training.
Task-5: Compile all documentation, insights, and findings into a well-structured report and share it with stakeholders or publish it for broader accessibility.